## Sample board goals
[Your Organization] Board action plan
What we'll accomplish | When (deadline, quarter, meeting date, etc) | Success measures | Who's responsible (committee, ad-hoc group, point person, etc.) | Who gives input/feedback | Status
Elect 2-3 new board members | Board meetings: solicit prospect names Ongoing: prospect cultivation & vetting Ongoing: nominating | Two to three new board members that provide needed skills and/or representation | Board Development | Board and sstaff leadership | Ongoing
Complete strategic plan | 2024-03-01 | Board approved | Strategic planning committee | board, staff | In progress
Launch Advisory Board | Q1 | Minimum 4 members - 2 info meetings | Board Development |  | Completed Q4
Deepen of JEDI principles into board mindset and operations | Q1: set annual goals Q1: conduct baseline assessment Q2: learning session Q2: begin integrating BJEDI into committee work Q2: board meeting discussion Q3: board meeting discussion Q4: board meeting discussion | All board members are engaged and supporting JEDI work. Jedi is integrated into board policies, prodedures, plans, decision making, and activities. | JEDI committee (Chair Dan, Amy, Ellie, Paula) | ED, board members | Annual goals: DONE Creating assessment: DONE Conduct baseline assessment: DONE Begin integration into other committees: Beginning Learning session: DONE
Provide support and management of E.D. | Q2: set annual goals Q2: feedback Q3: feedback Q4: annual evaluation | E.D. and board satisfaction with support and feedback | Governance committee (Victor, Ellie) | President | 2023 evaluation: in process
Strong board representation at events | Ongoing: markets Q3: Gala | Board representation at all key events | President |  | Ongoing
Support and amplify fundraising efforts | Q2: Major donor culivation & stewardship Q3: Promote gala and attend Q4: Support staff with year-end campaign Q4: Achieve 100% board giving | Completed calls and meetings with new major donor prospects and existing major donors--Dave Board members sharing gala event within their networks (social media, email, in-person), attend event themselves. Write notes on letters, if needed. Donate! All board members have made or brought in a financial contribution by the end of the year | Fundraising committee (Chair Esteve, Dave, Ellie) |  | Ongoing Will start when tickets go on sale 4th quarter Ongoing
Board Chair succession planning | Q3-Q4 | Plan in place for 2025, | Governance committee | All board members
Invite new potential donors (individual or corp) onsite | Q1-Q4 | Minimum of 10 for the year | All board members, Donor Relations Manager
Draft and deploy Board self-survey | Q3-Q4 | Completed survey by EOY | Governance committee | All board members | Ellie has surveys to use, if needed
Update documents:Board Skills matrix Board Recruitment Process Application of Interest Board Member Expectations Prospect Assessment Candidate Interview Guide | Q3 | All docs reviewed and updated as needed | Board Development
Funding Operating reserve (maintain 3 month coverage) | EOY | 3 month reserve post 2024 EOY | Finance Committee/staff | Finance Committee | DONE
Financial Policy review and updates | Q1 | Updated policies | Finance Committee/staff | Business Mgr, ED, Committee | DONE: Finance committee reviewed changes and approved the Financial Policy document at its March 19 meeting; full board approved at March 25 meeting.
Approved Investment policy | Q2 (moved from Q1) | Approved by board | Finance Committee/staff | Business Mgr, ED, Committee | DONE
Complete a successful audit | Q3 | Audit completed | Staff | Treasurer | IN PROCESS. AS OF JULY 30, LINDA HAD SUPPLIED ALL REQUESTED REPORTS AND DOCUMENTS TO THE AUDITOR. SHE WILL HANDLE FURTHER REQUESTS FOR INFO AS THEY COME IN.
Add cash flow projections to financials | Q1 | Monthly financials | Staff |  | DONE: Linda added four months of cash projections to the February financial reports, and will do so monthly going forward.
Review target of 30% benefits | Q3 | Reviewed by November meeting | Finance Committee/staff |  | We added medical insurance to staff benefits beginning July 1, 2024. Will review total cost at the end of the year.
Review and update HR Policy through JEDI lens | Q4 | Approved by Committee | Staff | Committee | Defer to 2025.
[5 empty] | This work is licensed under a Creative Commons Attribution 4.0 International License. | ¦ trec.org

## Template board goals
[Your Organization] Board action plan
What we'll accomplish | When (deadline, quarter, meeting date, etc) | Success measures | Who's responsible (committee, ad-hoc group, point person, etc.) | Who gives input/feedback | Status
[5 empty] | This work is licensed under a Creative Commons Attribution 4.0 International License. | ¦ trec.org

## Governance Comm
Bounty & Soul 2024 Board action plan
What we'll accomplish | When (deadline, quarter, meeting date, etc) | Success measures | Who's responsible (committee, ad-hoc group, point person, etc.) | Who gives input/feedback | Status
Document & Formalize the ED review process | Q2 | Completed & distributed plan | Governance | All board members
Board Chair succession planning | Q3-Q4 | Plan in place for 2026 | Governance & Exec committee | All board members
Draft and deploy Board self-survey | Q3-Q4 | Completed survey by EOY | Governance committee | All board members
Review by-laws for updates needed | Q3 | Report to Board on any changes | Governance Committee | All board members
[5 empty] | This work is licensed under a Creative Commons Attribution 4.0 International License. | ¦ trec.org

## Fund Dev Comm
Bounty & Soul 2024 Board action plan
What we'll accomplish | When (deadline, quarter, meeting date, etc) | Success measures | Who's responsible (committee, ad-hoc group, point person, etc.) | Who gives input/feedback | Status
Achieve 100% board giving participation | Q4 | All board members have made or brought in a financial contribution by the end of the year | Fundraising committee (Chair Ellie, Esteve, Dave, Tracey) |  | Ellie will get update on current status from staff
Major donor cultivation & stewardship
Lower level donor outreach
Promote Farm to Fork
[5 empty] | This work is licensed under a Creative Commons Attribution 4.0 International License. | ¦ trec.org

## JEDI Comm
Bounty & Soul 2024 Board action plan
What we'll accomplish | When (deadline, quarter, meeting date, etc) | Success measures | Who's responsible (committee, ad-hoc group, point person, etc.) | Who gives input/feedback | Status
Review this year's JEDI plan | Jan | Board members are prepared to discuss the plan at the Jan Board meeting and provide substantive feedback on the plan | JEDI Comm
JEDI Board member assessment | Jan - Mar | 100% Board participation in assessment survey | Dan
"Finding Common Ground" session | April | 100% attendance to the session. Board members have a shared understanding of: 1. Basic definitions and application of justice, diversity, equity, and inclusion 2. Why JEDI is crucial to our work and mission 3. Basic requirements of us as individuals to do this work together | Facilitator, JEDI Comm
Q3 Board JEDI exploration and discussion | Aug | Board members able and willing to engage in thoughtful and potentially challenging conversations. Increased open communication and understanding of food justice, systemic oppression, and how we works to disrupt food injustice as a system of inequity and oppression | JEDI Comm
Q4 Board JEDI exploration and discussion | Nov | Board members able and willing to engage in thoughtful and potentially challenging conversations. Increased open communication and understanding of food jinustice, systemic oppression, and how we works to disrupt food injustice as a system of inequity and oppression | JEDI Comm
Review 2025 JEDI plan | 2023-01-25 | Board members are prepared to discuss the plan at the Jan Board meeting and provide substantive feedback on the plan | JEDI Comm
JEDI Board member assessment | 2023-01-25 | 100% Board participation in assessment survey | Dan
[5 empty] | This work is licensed under a Creative Commons Attribution 4.0 International License. | ¦ trec.org

## Finance Comm
Bounty & Soul 2024 Board action plan
What we'll accomplish | When (deadline, quarter, meeting date, etc) | Success measures | Who's responsible (committee, ad-hoc group, point person, etc.) | Who gives input/feedback | Status
Funding Operating reserve (maintain 3 month coverage) | EOY | 3 month reserve post 2024 EOY | Finance Committee/staff | Finance Committee | On-going
Financial Policy review and updates | Q1 | Approved by board | Finance Committee/staff | Business Mgr, ED, Committee | completed
Approved Investment policy | Q1 | Approved by board | Finance Committee/staff | Business Mgr, ED, Committee
Complete a successful audit | Q2 | Audit completed | Staff | Treasurer | In progress
Add cash flow projections to financials | Q1 | Monthly financials | Staff |  | completed
Complete risk management assessment | Q4 | Approved by Committee & Board | Staff | Committee
Business model based on Strategic Plan | Q4 | Approved by Committee & Board | Staff | Committee
Review target of 30% benefits | Q4 | Reviewed by November meeting | Finance Committee/staff
Review and update HR Policy through DEIB lens | Q4 | Approved by Committee | Staff | Committee
[5 empty] | This work is licensed under a Creative Commons Attribution 4.0 International License. | ¦ trec.org

## Board Development Comm
Bounty & Soul 2024 Board action plan
What we'll accomplish | When (deadline, quarter, meeting date, etc) | Success measures | Who's responsible (committee, ad-hoc group, point person, etc.) | Who gives input/feedback | Status
Elect 2-3 new board members | Board meetings: solicit prospect names Ongoing: prospect cultivation & vetting Ongoing: nominating | Two to three new board members that provide needed skills and/or representation | Board Development | Board and staff leadership | Ongoing
Launch Stewardship Board | Q1 | Minimum 4 members - 2 info meetings | Board Development |  | In process
Update Orientation Guide | Q2 | Complete and post in Google Docs | Staff | Staff and Committee
Update documents:Board Skills matrix Board Recruitment Process Application of Interest Board Member Expectations Prospect Assessment Candidate Interview Guide | Q3 | All docs reviewed and updated as needed | Board Development
[5 empty] | This work is licensed under a Creative Commons Attribution 4.0 International License. | ¦ trec.org